## Sheet1
date | name | Task
2023-07-08 | Pratik | Our project is about online food ordering system. We will have a page where user can select food category. Another page where user can selct the menu. And the payemnt processing page. We will follow linear sitemap
2023-07-09 | Sudan | Researched and looked into the sample design for the website.
2023-07-09 | mazlum | Researched and looked into the sample design for the website.
2023-07-09 | Rodrigo | Researched and looked into the sample design for the website.
2023-07-09 | Ashish | Researched and looked into the sample design for the website.
2023-07-09 | Pratik | Created a github repository to enable everyone to collaborate in the project
2023-07-12 | Pratik,Sudan | Created wireframe
2023-07-13 | whole group | Image collection, theme selection
2023-07-15 | Mazlum | working on "Contact us" page
2023-07-16 | Rodrigo, Ashish | worked on Homepage
2023-07-18 | Pratik | created sitemap
2023-07-18 | Ashish, Rodrigo | cretaed About us page
2023-07-19 | Mazlum | completed Contact us page
2023-07-20 | Sudan, Pratik | working on Confirm page
2023-07-23 | Pratik | completed the "order_complete" page
2023-07-26 | Rodrigo,sudan | created product index page
2023-07-27 | Pratik | created product detail page
2023-07-28 | Mazlum, rodrigo | created tablet, mobile wireframe
2023-07-28 | Ashish | working on documentation
2023-07-30 | Rodrigo | made Cart Page
2023-08-01 | Ashish | Commenting and documentation
2023-08-02 | Pratik, Sudan, Mazlum
2023-08-02 | Pratik | bug fixes
2023-08-05 | Pratik | Compiled files for submission